## Task List
Shagun — Track B task list (HFB Proactive AI Chatbot)
Track B = conversation, config & reporting. Prasad owns Track A (event/trigger pipeline + platform). See POA/18 for the full split.
Task ID | Task | POA reference | Phase | Status | Started | Completed | What I did (fill in on completion) | Files / evidence
S3 | Conversation-intent scenarios + scripted trees (17 intents) | POA/16 §16.4, §16.6 | Sprint 0 | DONE | 2026-09-01 | 2026-09-01 | Built IntentScenarioComposer with one scripted tree per mandated intent — depth varied by structural distinctness (single-turn lookup, multi-turn slot filling, out-of-scope refusal, ambiguity->clarify, and CV-17 mid-conversation requirement change as a real branching tree). Shipped BOTH halves of the §16.6 Phase-2 seam: ReplySource protocol (ScriptedReplySource for Phase 1) and Evaluator protocol (ExactExpectationEvaluator, judges a transcript not the script so it survives LLM-generated replies). All claims grounded in the same World the booking-API mock reads. Split delivered_excludes (claim WRONG vs live data, must never be delivered) from superseded_tokens (claim CORRECT when said, then obsoleted — must not reach the final confirmation); conflating them made one of the two cases silently stop testing anything. | generator/intents.py (new), models.py, pipeline.py, cli.py, tests/test_conversation_intents.py — 73 tests green. Reverted then restored 2026-09-01; in the tree and green. Local only, not pushed.
S4 | PII redaction fixtures — obvious + embedded PII | POA/16 §16.5 | Sprint 0 | Not started
S6 | Future-client-compat layer — repository interface, field_map.yaml, lenient DTO | POA/16 §16 item 6 | Sprint 0 | Not started
B1 | Admin Console & Trigger Configuration — persistence + CRUD | POA/13 | Track B | Not started |  |  |  | NOTE: the config CONTRACT already exists (TriggerConfig, RoutingRule, FrequencyCap, Deferred in generator/models.py + defaults in fixtures.py). This task owes persistence + admin CRUD, not the schema. RoutingRule.match/.route/.sla are bare dicts to tighten.
B2 | Conversation Orchestrator (context + personalisation) | POA/08 | Track B | Not started
B3 | LLM Integration & Fallback Service | POA/09 | Track B | Not started
B4 | Claim Verification Service | POA/10 | Track B | Not started |  |  |  | booking-API mock already built — ready to start any time.
B5 | Chatbot UI Integration (HS-103) + admin UI | POA/11 | Track B | Not started |  |  |  | HS-103 mock already built.
B6 | Customer Response & Multi-turn Conversation Manager | POA/12 | Track B | Not started |  |  |  | Consumes the S3 trees. Must honour delivered_excludes vs superseded_tokens as two different rules.
B7 | Audit, Reporting & Analytics | POA/14 | Track B | Not started
P1 | Two-person work split + daily git workflow (POA/18) | POA/18 | Process | DONE | 2026-08-31 | 2026-09-01 | Wrote POA/18: split the module dependency graph into two tracks so no module gets built twice, mapped cross-track contract points, and defined the daily push/merge routine. Corrected an early error in it — B1 does NOT block Prasad's A5/A6/A8, because the M13 contract already exists. Confirmed track ownership after Prasad accepted Track A. | POA/18_Team_Work_Split_and_Git_Workflow.md + POA/00 index row. Reverted then restored 2026-09-01; in the tree. Local only, not pushed.
P2 | Agree git workflow (POA/18 §6) with Prasad | POA/18 §6 | Process | Blocked |  |  |  | Waiting on Prasad. §6 still describes per-person branches while we push to main.
P3 | Agree service-code repo layout (services/*) with Prasad | POA/18 §8.2 | Process | Blocked |  |  |  | Waiting on Prasad. Blocks B1 scaffolding. No POA specifies a layout yet.

## Work Log
Work log — one row per working session
Add a row every day. This is what shows the effort; Status on sheet 1 is only a flag.
Date | Task ID | What I did | Outcome / proof | Pushed
2026-08-31 | P1 | Read the whole repo and all 18 POA files. Wrote POA/18: cut the module dependency graph into two tracks that live in separate directories, so parallel work merges additively instead of colliding. Added Sprint-0 file-level split, cross-track contract points and a status tracker. | POA/18 created, indexed in POA/00 | d1f6987
2026-09-01 | P1 | Prasad accepted Track A. Marked ownership CONFIRMED in POA/18 and closed open question 1. | POA/18 v1.1 | 3f444b8
2026-09-01 | S3 | Built the 17 scripted conversation trees, the ReplySource seam, world-grounded claims, and the pipeline/CLI wiring to write them to test_data/conversations/. | 23 new tests, 66 total green | 9840cb0
2026-09-01 | S3 | Fixed a contract bug found in review: delivered_excludes was carrying two incompatible meanings. Split out superseded_tokens, added the Evaluator half of the §16.6 Phase-2 seam, promoted path()/paths()/all_turns() so there is only one definition of a path, and extended the tree-wide invariants to cover branch turns (they were escaping world-grounding). | 73 tests green | 78aedf0
2026-09-01 | — | Reverted all five commits (POA/18 + S3 + tracker) at Shagun's request. Used git revert rather than a force-push so history stays intact and Prasad's clone is unaffected. Working tree verified byte-identical to 67b977c; 43 tests green. New standing rule from here: all work stays LOCAL, nothing goes to GitHub unless explicitly asked. | Tree == 67b977c, 43 tests green | local only
2026-09-01 | S3 / P1 | Restored both reverted deliverables locally at Shagun's request — S3 first, then POA/18. Restored at file level from 78aedf0 / b54edb8 rather than by reverting the revert, so each came back independently and history stays readable. Restoring POA/18 also re-validated the 'see POA/18 §4' pointer in generator/models.py, which was dangling in between. | Working tree == b54edb8 (plus tracker improvements); 73 tests green | local only

## Reference
Reference — split, shared files, open questions
THE SPLIT
Prasad — Track A | Event & trigger pipeline + platform: POA 01-07, 15. Sprint 0: S1, S2, S5.
Shagun — Track B | Conversation, config & reporting: POA 08-14. Sprint 0: S3, S4, S6.
SHARED FILES — announce before pushing
generator/models.py | Both tracks need it. Append one bounded contiguous block; never rename or remove a field the other track uses.
generator/pipeline.py | Both add writers. Keep the diff to contiguous appended lines.
tests/conftest.py | Keep new fixtures in your own test module unless genuinely shared.
OPEN — waiting on Prasad
Git workflow (POA/18 §6) | Doc says per-person branches; we are pushing to main. Needs a decision.
Repo layout | services/platform, services/event_pipeline, services/conversation — unconfirmed.
OPEN — needs the client (POA/00 §7)
LLM provider & data residency | Which model, which region, Hertz constraints.
Booking API | One service or several? Latency SLA?
HS-103 surface | REST, websocket or embedded widget SDK?
Support/agent queue | Zendesk, Salesforce or in-house?
WORKING RULES
Everything stays local | No pushes to GitHub. Commit locally only, unless Shagun explicitly asks in that moment. origin/main is still at b54edb8; the revert commit is local and un-pushed.
Sheet updates automatically | After every completed task: update this sheet and open it. No need to ask.
HOW TO USE THIS FILE
On starting a task | Set Status to 'In progress' and fill Started.
On finishing | Set Status 'DONE', fill Completed, and write What I did + Files/evidence.
Every session | Add a Work Log row — the log is what shows effort, the status is only a flag.
Regenerate | python build_task_tracker.py (overwrites this file — edit the script, not just the sheet, if you want changes to survive)