## Task List
Prasad — Track A task list (HFB Proactive AI Chatbot)
Track A = event & trigger pipeline + platform. Shagun owns Track B (conversation, config & reporting). See POA/18 for the full split.
Task ID | Task | POA reference | Phase | Status | Started | Completed | What I did (fill in on completion) | Files / evidence
S1 | Expand taxonomy & stations — 12 classes, city/suburban, one-way | POA/16 §16.2 | Sprint 0 | DONE | 2026-09-01 | 2026-09-01 | Expanded to the full 12-class Hertz-style ACRISS taxonomy and added city/suburban stations plus a new US/USD region and domestic one-way support. KEY DECISION: added the 8 new classes and 6 new stations in a purely ADDITIVE world pass-3, so passes 1 & 2 keep their exact RNG draw sequence and the 7 golden-scenario prices stay byte-identical — proven by recomputing them against origin/main in a throwaway worktree (LHR/ICAR=52.21, MAN/ECAR=31.47, FRA/FCAR=60.63). Kept the legacy generic 'SUV' code for backward-compat with the existing golden fixtures rather than renaming it (a rename would shift the RNG and move the prices). One-way is domestic-only (cross-border needs approval per the policy). Rewrote the per-location currency test to be country-driven so future stations don't break it. | generator/world.py, catalogues.py, config.py, models.py (LocationType.suburban); tests/test_taxonomy_stations.py (8). Commit 73dde84 (pushed track-a, PR #1)
S2 | Fee completeness — late-return, no-show, fuel + dispute scenarios | POA/16 §16.1 | Sprint 0 | DONE | 2026-09-01 | 2026-09-01 | Added itemised, disputable fees. KEY DECISION: post-rental charges (late-return, no-show, fuel) are recorded as separate FeeLine rows and deliberately NOT folded into the quoted total, so 'why was I charged more than I was quoted?' disputes are realistic; the one-way fee, which IS known at booking, does go into the total. Modelled no-show as a first-class BookingStatus. Put the fee amounts in a single fee_rules() source of truth so generated bookings, the dispute fixtures and the policy text can't drift apart. Shipped 5 hand-authored dispute fixtures (FeeDisputeComposer) with pinned resolutions covering upheld / refunded / partial-refund / escalated-to-human, each grounded in the same world the bot verifies against. | generator/customers.py, durations.py (late_return_extra_days), scenarios.py (FeeDisputeComposer), catalogues.py (fee_rules), models.py (FeeLine/FeeType/FeeDispute/DisputeResolution, Booking.one_way_fee/fees, BookingStatus.no_show); tests/test_fees_and_disputes.py (7). Commit 73dde84
S5 | Load / SLA config knobs — eps, concurrency, mock timeouts | POA/16 §16.3 | Sprint 0 | DONE | 2026-09-01 | 2026-09-01 | Turned the resolved §16.3 load/SLA numbers into explicit config knobs rather than magic numbers: a LoadProfile on GenConfig (10/50/100 eps; 500/1000 concurrent; <2s no-call / <5s tool-backed SLA; 5s deterministic mock timeout), exposed via VolumeSampler.load_summary and written to config/load_profile.yaml so the soak/load harness reads one source of truth. | generator/config.py (LoadProfile), volume.py, pipeline.py, models.py (Dataset.load_profile); tests/test_load_config.py (4). Commit 73dde84
A1 | Platform skeleton — repo layout, CI, secrets, logging/tracing baseline | POA/15 | Track A | DONE | 2026-09-01 | 2026-09-01 | Started Track A service code. Ratified the services/ monorepo layout (resolves POA/18 §8.2, recorded in POA/15 §12) and built the shared services/platform template: create_app(name) returns a FastAPI app with structured JSON logging + per-request correlation id, Prometheus /metrics, an OpenTelemetry tracing SEAM (off unless HFB_OTEL_ENABLED + libs present, so no hard OTel dep yet), /healthz + /readyz with pluggable readiness checks, and problem+json error handling. Data seams (Postgres/Redis/Celery) are lazy factories, so the skeleton needs none of those deps installed — A2/A7 add them. services/event_pipeline boots on the template (A2-A8 mount here). Env-driven HFB_* config, no secrets in code. | services/platform/*, services/event_pipeline/*, docker-compose.yml, Dockerfile, .github/workflows/ci.yml (pytest matrix + ruff), .env.example, POA/15 §12; tests/test_platform_skeleton.py (8) — 100 total green, ruff clean. Commit 4a1ed3d (PR #1)
A2 | Event Store — Postgres + Redis Streams | POA/03 | Track A | In progress | 2026-09-01 |  | Core done + downstream-ready. Built services/event_pipeline/store/: append-only events table + transactional event_outbox (POA/03 §3.1); idempotent write_event that inserts both in ONE transaction (existence check + IntegrityError backstop, never double-enqueues); an OutboxRelay that publishes THEN marks per-row (at-least-once, consumers dedupe on event_id) — property-tested for no-loss under a flaky publisher; a Redis StreamPublisher (XADD events:in + ensure_group trigger-eval) behind a protocol so it's tested with no Redis; read models recent_events/session_events/last_event_at/has_repeated_search (signal I). Wired a postgres readiness check + app.state.event_store (A4 writes through it). Portable schema runs on Postgres (JSONB, bigserial) in prod and in-memory SQLite in tests. DEFERRED (POA/03 §11): retention/partition job, signal-J booking backfill, live-Redis integration; sync (not async) + create_all bootstrap instead of Alembic, both by design. | services/event_pipeline/store/{tables,store,publisher,relay,bootstrap}.py, main.py; services/requirements.txt, pyproject, POA/03 §11; tests/test_event_store.py (12) — 112 total green, ruff clean. Commit d8fc10b (pushed track-a, PR #1)
A6 | Frequency Cap & Precedence Engine | POA/05 | Track A | In progress | 2026-09-01 |  | Core done + tested. services/event_pipeline/frequency/: Postgres engagement ledger (source of truth; only reserved/confirmed count, rolled_back ignored), sliding-window caps that DELEGATE to reference.would_fire (so the service and the invariant suite test the same rule), per-customer global cap + ISO-8601 cooldown, deterministic precedence (weight -> match specificity -> most-recent signal -> lowest id, order-independent), atomic reserve under a per-customer lock (concurrency test: 10 threads, cap 1 -> exactly 1 fires). reserve->confirm/rollback so a failed M08 send frees the slot instead of burning the cap. Every suppression carries a reason + per-trigger losers for M14. CROSS-TRACK: A6->M08 contract (MatchCandidate/EngagementDecision/SuppressionReason) added to generator/models.py — reconcile with Shagun's local §5 handshake. Deferred (POA/05 §11): Redis counters, reservation-TTL sweep, M13 cap config. No HTTP surface (library called by A5). | services/event_pipeline/frequency/{tables,ledger,engine,precedence,lock,bootstrap}.py, generator/models.py (contract), POA/05 §11; tests/test_frequency_precedence.py (11) — 134 total green, ruff clean. Commit 7a5a0f8 (PR #1)
A4 | Event Ingestion API (FastAPI) | POA/02 | Track A | In progress | 2026-09-01 |  | Core done + tested. The single write-door in services/event_pipeline/ingestion/: POST /v1/events + POST /v1/events:batch (partial-success) writing through A2's transactional outbox. Single-event body IS generator.models.Event, so FastAPI validation + extra='forbid' is the PII field allow-list (POA/15 §4) — unknown/PII field -> 422. Auth, identity binding and rate limiting sit behind seams because §10 is open: ApiKeyAuthenticator now (mTLS/JWT later; JWT would set Principal.customer_id so identity binding becomes a real cross-check), in-memory fixed-window rate limiter (Redis in prod). Idempotency delegated to the store (retry -> 202 duplicate, never a second row). Outcome->status 202/409/429/503/422. build_app wires it when a store is present + accepts an injected store for tests. Deferred (POA/02 §11): real auth mechanism, distributed rate limiter, load verification. | services/event_pipeline/ingestion/{router,service,auth,ratelimit,schemas}.py, main.py, services/platform/config.py, pyproject (ruff), POA/02 §11; tests/test_ingestion_api.py (11, incl. e2e API->store->relay->stream) — 123 total green, ruff clean. Commit ee06657 (PR #1)
A5 | Trigger Evaluation Engine | POA/04 | Track A | In progress | 2026-09-01 |  | Core done + tested. The node-N brain in services/event_pipeline/triggers/. Sandboxed field/op/value rule DSL (eq/ne/in/not_in/gt/gte/lt/lte/exists over dotted paths, no eval, §8). Node-N routing: idempotency guard -> match active rules -> deferred matches to DeferredSink (M06/A7), in-session matches to A6.reserve; approved -> FireMessage on FireSink (M08/B2), suppressed -> SuppressionSink (Z1/M14), no match -> dropped. Contracts are messages to sinks not direct calls (§5); FireMessage (generator/models.py) carries A6's reservation_id. RedisTriggerConsumer (XREADGROUP events:in/group trigger-eval -> evaluate -> XACK) + parse_stream_fields; end-to-end store->relay->parse->evaluate->fire tested with no Redis. Deferred (POA/04 §11): I/J derivation workers (need A7), rule hot-reload, handoff branch (§10.3), consumer partitioning. | services/event_pipeline/triggers/{dsl,evaluator,consumer,sinks}.py, generator/models.py (FireMessage), POA/04 §11; tests/test_trigger_evaluation.py (12) — 146 total green, ruff clean. Commit 2b46310 (PR #1)
A3 | Customer Journey & Behavioural Event Capture (SDK / contract) | POA/01 | Track A | Not started |  |  |  | Depends on the A4 contract, not the whole service.
A7 | Pending-Engagement Queue & Deferred Scheduler (Celery) | POA/06 | Track A | In progress | 2026-09-02 |  | Core done + tested. services/event_pipeline/pending/: pending_engagements queue where PendingQueue.enqueue IS A5's DeferredSink (so A5's deferred matches flow straight in, no duplication). eligible_at = created + wait_period, expires_at = created + expiry; every read takes an explicit `now` so wait/eligibility/expiry are time-travel tested. expire_due sweeps overdue pending -> expired (returns ids for Z2), never touching raised/raising; reconcile_stuck releases crashed `raising` rows. Login re-eval (node S): on_login under a per-customer lock fetches eligible entries, arbitrates them through A6 (multiple pending compete on PRECEDENCE, §10.3), fires the winner via FireSink + marks raised; losers/cap-suppressed stay pending for a later login. Concurrency test: 5 parallel logins raise at most once. Celery Beat wiring (beat_schedule + register_pending_tasks) with no top-level celery import. e2e A5->A7->A6 tested. Deferred (POA/06 §11): in-session merge at login, SKIP-LOCKED claim, Beat integration run. | services/event_pipeline/pending/{tables,queue,scheduler,tasks,bootstrap}.py, services/requirements.txt + pyproject (celery), POA/06 §11; tests/test_pending_queue.py (12) — 158 total green, ruff clean. Commit 10285b5 (PR #1)
A8 | Human Handoff Manager | POA/07 | Track A | Not started |  |  |  | NEXT. Depends on A5 (done). Keep handoff code THIN around RoutingRule .match/.route/.sla dicts — B1 will likely tighten them into real models. Handoff event is a message contract, not a call (§5). Routing defaults already in generator/fixtures.default_routing_rules().
P1 | Accept Track A + maintain POA/18 §7 status rows | POA/18 | Process | DONE | 2026-09-01 | 2026-09-01 | Accepted Track A ownership (event/trigger pipeline + platform, POA 01-07 & 15). Maintain my own A- and Sprint-0 rows in the shared POA/18 §7 status table. (POA/18 itself authored by Shagun.) | POA/18 §7 (my rows)
P3 | Ratify service-code repo layout (POA/18 §8.2) | POA/18 §8.2 | Process | DONE | 2026-09-01 | 2026-09-01 | RESOLVED from my side: chose the services/ monorepo — services/platform (shared template), services/event_pipeline (Track A), services/conversation (Track B). Recorded it in POA/15 §12 and marked POA/18 §8.2 RESOLVED. This unblocks B1 scaffolding for Shagun. | POA/15 §12, POA/18 §8.2. Commit 4a1ed3d
P4 | Deterministic test_data — seed event ids + regenerate | design principle P4 | Process | DONE | 2026-09-01 | 2026-09-01 | The committed test_data churned on every `generator build` because golden + volume event ids used uuid4. Replaced them with a seeded UUIDv5 (rng.stable_uuid) keyed on stable fields, proved two independent regens are byte-identical, then regenerated test_data as the canonical snapshot — which also wrote Shagun's S3 conversations/ output for the first time (deterministic, so a Track B regen reproduces it identically, no conflict). | generator/rng.py, scenarios.py, patterns.py; test_data/*. Commits da93227, 2eeea2b
P2 | Follow git workflow (POA/18 §6) + PR into main | POA/18 §6 | Process | In progress | 2026-09-01 |  | Following §6: long-lived branch track-a/event-pipeline, merge (not rebase) main in at day-end, PR into main (PR #1 open), no force-push. TO RECONCILE with Shagun: §6 describes per-person branches, but Shagun is currently keeping everything LOCAL/un-pushed — the two conventions need to agree. | branch track-a/event-pipeline, PR #1

## Work Log
Work log — one row per working session
Add a row every day. This is what shows the effort; Status on sheet 1 is only a flag.
Date | Task ID | What I did | Outcome / proof | Pushed
2026-08-27 | foundation | Prior sessions (pre-split): built the generator/mocks/tests foundation and POA 00-17 — the seeded reference world, Pydantic contract models, 7 golden verification scenarios, and the v0.2 SME business domain (companies/rate-plans/invoices, booking lifecycle, van classes, protection/extras/policy catalogues) driven by the POA/17 audit. This is the shared foundation both tracks build on — the reason I own Track A. | 43 tests green; generator v0.2 | 78c7d3b, 315ab9c
2026-09-01 | S1/S2/S5 | Implemented Sprint 0 Track A. S1: 12-class taxonomy + city/suburban/US stations + one-way via an additive world pass-3 that keeps the golden prices byte-identical (verified against origin/main). S2: one-way/late-return/no-show/fuel fees + 5 pinned dispute fixtures, with post-rental charges kept OUT of the quoted total so disputes are realistic. S5: LoadProfile knobs from the §16.3 targets. Contract changes to models.py were additive/optional only. | 19 new tests, 92 total green | 73dde84
2026-09-01 | P4 | Found the committed test_data churned on every regen because golden + volume event ids used uuid4. Replaced them with a seeded UUIDv5 keyed on stable fields, proved two independent regens are byte-identical, then regenerated test_data as the canonical snapshot (which also wrote Shagun's S3 conversations/ output for the first time — deterministic, no future conflict). | regens diff-clean; 92 green | da93227, 2eeea2b
2026-09-01 | A1 / P3 | Ratified the services/ monorepo (POA/15 §12) and built the A1 platform skeleton: services/platform template (create_app wiring logging/correlation-id/metrics/OTel-seam/health/readyz/errors + lazy pg/redis/celery factories), a booting services/event_pipeline app, docker-compose (pg+redis+service), Dockerfile, GitHub Actions CI, .env.example. Installed the service runtime deps and kept the heavier infra deps lazy. | 8 new tests, 100 total green; ruff clean; /healthz /readyz /metrics all 200 | 4a1ed3d (PR #1)
2026-09-01 | tracker | Reviewed Shagun's new 3-sheet tracker (Docs/Shagun_Task_Tracker.xlsx), my own tracker and POA/18, then rebuilt my Track A tracker to match Shagun's format (Task List / Work Log / Reference) via build_prasad_tracker.py. | Docs/Prasad_TrackA_Task_Tracker.xlsx regenerated | local
2026-09-01 | A2 | Built the Event Store on the A1 platform template. Followed the project's delegate-to-the-spec discipline (persists generator.models.Event, so the generated dataset round-trips) and the transactional-OUTBOX pattern rather than a dual write — the whole exactly-once argument is publish-then-mark ordering. Made it testable without infrastructure the way Shagun did for B4: portable schema (JSONB/bigserial on Postgres, JSON/rowid on SQLite) + an injected stream publisher, so 12 tests incl. the §7 no-loss property run on in-memory SQLite with no Docker. One real bug the tests caught: a BigInteger outbox PK doesn't autoincrement on SQLite (only INTEGER PRIMARY KEY is the rowid alias) — fixed with with_variant. Scoped POA/03 §11 honestly: retention/partition + signal-J backfill + live-Redis deferred. | 12 new tests, 112 total green; ruff clean | d8fc10b (PR #1)
2026-09-01 | A4 | Built the Ingestion API — the single write-door — on the A1 template, writing through A2's outbox (so no direct dual write). Kept the same discipline: the body IS the Event contract, so validation + extra='forbid' doubles as the PII field allow-list, and idempotency is the store's not a second mechanism. The §10 open questions (auth mechanism, identity token vs body, volume) are handled behind seams — API-key auth, identity binding, in-memory rate limiter — the way Shagun handled B4/B5's open transport, so none of them block code. Batch endpoint does per-item validation for partial success. Added an injected-store path to build_app for tests and an end-to-end test proving API->store->outbox->relay->stream. | 11 new tests, 123 total green; ruff clean | ee06657 (PR #1)
2026-09-01 | A6 | Built the Frequency Cap & Precedence engine — the gate A5 calls before firing. Same delegate-to-the-spec discipline as A2/A4: cap accounting hands ledger timestamps to reference.would_fire, the exact sliding-window rule test_invariants already asserts, so the service can't quietly diverge from the spec. Precedence is deterministic and order-independent (weight -> specificity -> recency -> id). The judgement call was the reserve->confirm/rollback handshake: a reserved slot is only finalised when M08 delivers, and rolled back on failure, so a failed send doesn't burn a customer's cap — the cross-track contract I put in generator/models.py to reconcile with Shagun's local §5. Wrote the concurrency invariant test POA/05 §6 asks for (10 threads, cap 1 -> exactly one fires) using a per-customer lock seam. | 11 new tests, 134 total green; ruff clean | 7a5a0f8 (PR #1)
2026-09-01 | A5 | Built the trigger engine — node N, the brain that ties A2, A6 and (eventually) M08 together. Kept A5 thin on purpose: matching is a small sandboxed field/op/value DSL (no eval), cap/precedence is delegated to A6, and every downstream is a message to a sink rather than a direct call (POA/18 §5) so Track B's M08 and my own A7 plug in without A5 changing. The fire decision is a shared FireMessage carrying A6's reservation_id, so the confirm/rollback loop reaches back to the cap. Added an idempotency guard so an at-least-once stream redelivery can't double-fire, and an end-to-end test that runs a real ingested event through store->relay->parse->evaluate->fire without needing Redis. Scoped POA/04 §11 honestly: the I/J derivation workers wait on A7, and the handoff branch on M07/§10.3. | 12 new tests, 146 total green; ruff clean | 2b46310 (PR #1)
2026-09-02 | A7 | Built the deferred branch — the pending queue + login re-evaluation. The clean win was making PendingQueue implement A5's DeferredSink, so A5's deferred matches flow straight in with no new contract, and on_login just re-arbitrates them through the SAME A6 engine — so precedence and cap behave identically whether a signal fires in-session or after a login. Kept it testable without a clock or a broker: every read takes an explicit `now` (so expiry/eligibility are time-travelled) and the Celery tasks are thin wrappers over pure methods with no top-level celery import. Wrote the two invariants the POA cares about — raised-at-most-once under concurrent logins, and expiry never touching a raised row. Answered §10.3 (pending entries compete on precedence, not FIFO). | 12 new tests, 158 total green; ruff clean | 10285b5 (PR #1)

## Reference
Reference — split, shared files, decisions, open questions
THE SPLIT
Prasad — Track A | Event & trigger pipeline + platform: POA 01-07, 15. Sprint 0: S1, S2, S5.
Shagun — Track B | Conversation, config & reporting: POA 08-14. Sprint 0: S3, S4, S6.
SHARED FILES — announce before pushing
generator/models.py | Both tracks need it. Append one bounded contiguous block; never rename or remove a field the other track uses. My Sprint 0 added optional fields/enums only — nothing renamed/removed.
generator/pipeline.py | Both add writers. Keep the diff to contiguous appended lines.
tests/conftest.py | Keep new fixtures in your own test module unless genuinely shared.
Golden prices are sacred | Any world change must keep the 7 golden-scenario prices byte-stable — use the additive-pass pattern (see S1).
DECIDED — from my (Track A) side
Repo layout | RATIFIED: services/ monorepo (platform + event_pipeline + conversation). Recorded in POA/15 §12; POA/18 §8.2 marked RESOLVED.
Git workflow | Track A on long-lived branch track-a/event-pipeline; merge (not rebase) main at day-end; PR into main (PR #1 open); no force-push. To reconcile with Shagun's current local-only rule.
OPEN — needs the client (POA/00 §7)
LLM provider & data residency | Which model, which region, Hertz constraints.
Booking API | One service or several? Latency SLA? (gates A-side claim inputs / B4.)
HS-103 surface | REST, websocket or embedded widget SDK?
Support/agent queue | Zendesk, Salesforce or in-house? (gates A8 handoff routing.)
HOW TO USE THIS FILE
On starting a task | Set Status to 'In progress' and fill Started.
On finishing | Set Status 'DONE', fill Completed, and write What I did + Files/evidence.
Every session | Add a Work Log row — the log is what shows effort, the status is only a flag.
Regenerate | python build_prasad_tracker.py (overwrites this file — edit the script, not just the sheet, if you want changes to survive)